## Cover Page & Instructions
The USA Staffing Roadmap provides an overview of features recently completed or planned for upcoming releases. Please note that new features will be added to this roadmap as they are accepted by the product team, and production delivery target dates will be added as they become known. All content is subject to change.
| Key |  |  | Instructions
| Future | ○○○ | There is an understood desire for these features, but formal planning has not yet begun for their development | 1. | View the Features tab to review the USA Staffing Roadmap.
| In Planning | ●○○ | Planning, design, and user research is underway regarding the problem it hopes to solve and the scope and feasibility of the feature, but it is not yet scheduled for development | 2. | Use the key to understand where the feature is in the development cycle.
| In Development | ●●○ | Currently in development by the USA Staffing technical team | 3. | Use filters to view the most pertinent content to your agency.
| Complete | ●●● | Currently available in USA Staffing | 4. | If you still have questions, contact your Account Manager.
| New Feature |  | A new feature since the latest version of the roadmap was published | 5. | To filter on your agency's requests, click the Interested Agencies filter dropdown, select Text Filters > Contains, and type your agency's acronym.
| Version | Date Published
| 9 | 2024-01-12
| 10 | 2024-02-09
| 11 | 2024-03-08
| 12 | 2024-04-05
| 13 | 2024-05-03
| 14 | 2024-06-07
| 15 | 2024-07-09
| 16 | 2024-08-02
| 17 | 2024-09-04
| 18 | 2024-09-27
| 19 | 2024-10-25
| 20 | 2024-12-13
| 21 | 2025-01-17
| 22 | 2025-02-28

## Features
Key
Future | ○○○
In Planning | ●○○
In Development | ●●○
Complete | ●●●
New Feature
Number | Name | Description | Phase | Area | Production Delivery Target | Interested Agencies
230711 | HDW – SME Evaluations | Enable reporting on the SME Evaluation assessment type within the hiring data warehouse. | ●●○ | Hiring Data Warehouse | 2024-10-31
250875 | Position Description Reviews Reporting | Add reporting to the Staffing Administration Data Package about Position Description Reviews. | ●●○ | Staffing Administration Data Package | 2024-10-31
245496 | Modify Task Owner and Onboarding Process Owner Assignments | Allow Onboarding users to select HR Task Owner & Onboarding Process Owner at Certificate Audit and select HR Task Owner at Workflow and Task Assignment in New Hire Record. | ●●○ | New Hire | 2024-11-14
325071 | HDW Infrastructure, Operations, and Maintenance | Update and tests to HDW infrastructure, as well as ongoing maintenance to Hiring Data Warehouse fields. | ●●○ | Hiring Data Warehouse | 2024-12-31
239383 | Update Filter Layout on Vacancy Dashboard | Enhance user experience and usability by replacing filters on the Vacancy dashboard with newly designed filter side drawer that contains expandable/collapsible sections. | ●●○ | Dashboard | 2025-01-09 | DOI; USDA; VA
244253 | USA Staffing System Status Page | Create a static URL, which customers can bookmark, that provides the current USA Staffing Production system status. This could expand to include all USA Staffing environments, as well as Hiring Data Warehouse and Cognos updates/outages. | ●●○ | System | 2025-03-01
244091 | Create Text Alert for New Hires TJO | Allow HR users to send a text message notification to new hires informing them of an update (TJO) along with a hyperlink for the new hire to take action. (Availability of this functionality will depend on additional development required by USAJOBS.) | ●●○ | Notifications | 2025-03-06 | Treasury
249610 | Designate Task Owner at Request Approval | Enable HR users to assign Task Owners and Onboarding Process Owners during the request approval process to enhance the coordination of work throughout the recruitment phase. | ●●○ | Request | 2025-04-17
354368 | Enable Full Form Visibility in Onboard on Mobile Device | Ensure the entire completed form is visible to new hires when previewing their forms for submission on a mobile device. | ●●○ | Onboarding | 2025-04-24
279331 | Mass Approval of Linked Requests | Provide HR specialists with a shortcut to quickly approve requests for additional selections that are associated with an existing vacancy. | ●●○ | Request | 2025-04-24 | DOI; IRS; Treasury
217536 | Add Multi-Select Filtering Options to Requests Dashboard | Modify the Requests dashboard filter interface to align with the drawer-based design on other dashboards and enable the selection of more than one item in certain drop-down filters. | ●●○ | Dashboard | 2025-04-25 | VA
188474 | Organizations API Entity | Rewrite & Deploy Organizations API Entity in Azure. | ●●○ | Data API | Q1 FY25
188475 | Offices API Entity | Rewrite & Deploy Offices API Entity in Azure. | ●●○ | Data API | Q1 FY25
325987 | Customers API Entity | Rewrite & Deploy Customers API Entity in Azure. | ●●○ | Data API | Q1 FY25
325982 | Certificates API Entity | Rewrite & Deploy Certificates API Entity in Azure. | ●●○ | Data API | Q1 FY25
325991 | New Hires API Entity | Rewrite & Deploy New Hires API Entity in Azure. | ●●○ | Data API | Q1 FY25
325967 | Announcements API Entity | Rewrite & Deploy Announcements API Entity in Azure. | ●●○ | Data API | Q2 FY25
325968 | Applicants API Entity | Rewrite & Deploy Applicants API Entity in Azure. | ●●○ | Data API | Q2 FY25
325973 | Assessments API Entity | Rewrite & Deploy Assessments API Entity in Azure. | ●●○ | Data API | Q2 FY25
325978 | Certificate Applications API Entity | Rewrite & Deploy Certificate Applications API Entity in Azure. | ●●○ | Data API | Q2 FY25
325997 | Onboarding Tasks API Entity | Rewrite & Deploy Onboarding Tasks API Entity in Azure. | ●●○ | Data API | Q2 FY25
326003 | Requests API Entity | Rewrite & Deploy Requests API Entity in Azure. | ●●○ | Data API | Q2 FY25
326007 | Reviews API Entity | Rewrite & Deploy Reviews API Entity in Azure. | ●●○ | Data API | Q2 FY25
326011 | Staffing Tasks API Entity | Rewrite & Deploy Staffing Tasks API Entity in Azure. | ●●○ | Data API | Q2 FY25
326013 | Vacancies API Entity | Rewrite & Deploy Vacancies API Entity in Azure. | ●●○ | Data API | Q2 FY25
253680 | Request App | Publish a Request App. | ●●○ | Power BI | Q2 FY25
253699 | Application App | Publish a Application App. | ●●○ | Power BI | Q2 FY25
253707 | Vacancy Announcement App | Publish a Vacancy Announcement App. | ●●○ | Power BI | Q2 FY25
253718 | Onboarding Status App | Publish a Onboarding Status App. | ●●○ | Power BI | Q2 FY25
244199 | Upgrade FootPrints Ticketing System | Maintain FootPrints, USA Staffing's help desk ticketing system, up to date with most recent stable version. | ●○○ | Users | 2025-02-15
276087 | USA Staffing Account Management Video Vignette | Add a video vignette that will provide narrated intructions for creating and managing accounts, explaining the difference between HM, HR, Onboarding, Reports Only, and AFD Only users. | ●○○ | Users | 2025-03-19
244200 | Hiring Manager Dashboard Chatbot | Add a chatbot that Hiring Managers can interact with for guided 24/7 assistance. | ●○○ | Users | 2025-04-01
244197 | Online Application Document Chatbot | Add a chatbot that applicants can interact with for guided 24/7 document assistance. | ●○○ | Users | 2025-09-30
244198 | Online Application Document Video Vignette | Add a video vignette that will provide narrated document guidance to reinforce existing online training and online help content. | ●○○ | Users | 2025-09-30
185656 | Time to Hire API Entity | Rewrite & Deploy Time to Hire API Entity in Azure. | ●○○ | Data API | Q1 FY25
100178 | Applicant Touchpoints App | Publish a Applicant Touchpoints App. | ●○○ | Power BI | Q2 FY25
253733 | Pipeline Management App | Publish a Pipeline Management App. | ●○○ | Power BI | Q2 FY25
251414 | Assessments App | Publish a Assessments App. | ●○○ | Power BI | Q2 FY25
251434 | Tasks App | Publish a Tasks App. | ●○○ | Power BI | Q2 FY25
251408 | Reviews App | Publish a Reviews App. | ●○○ | Power BI | Q2 FY25
251441 | Notes App | Publish a Notes App. | ●○○ | Power BI | Q2 FY25
116529 | Add Education Information | Allow HR users to collect school names in the online application using a standard data source to facilitate reporting. | ●○○ | Application | TBD | IC; NASA; Treasury
241140 | Enable Locations Preference Ranking | Allow HR users to collect applicants’ locations preference ranking in the online application. | ●○○ | Application | TBD | IRS; Treasury
245286 | Mass assign/update Task Owner, Due Date, and Status from Tasks Dashboard | Enable users to assign/update a Task Owner, Task Due Date, and Task Status for a group of tasks from a single location. | ●○○ | Dashboard | TBD | DHS; IRS; Treasury; VA
254126 | Candidate Inventory Notification to HR | Allows Hiring Managers to specify the Series, Grade, Pay Plan, and Location in which they are requesting to hire a candidate and populate that information in the email sent to HR. | ●○○ | Hiring Manager | TBD
261403 | Add Announcement Entries to Hiring Manager Request Event Log | Adds Announcement Open, Closed, and Removed information to the Hiring Manager Request Event Log. | ●○○ | Hiring Manager | TBD | DOC
187731 | Create an Applicant Count API | Allow agencies to retrieve a real-time count of applicants who have submitted an application. | ●○○ | Interconnections | TBD
254122 | Add Request Status Options | Emhance request statuses to allow HR, HM, and Onboarding users have a full understanding of what occurred with the request. | ●○○ | Request | TBD | DOI; IRS; Treasury
153321 | Enable Consolidated Filterable Certificate | Allow Hiring Managers a choice of viewing each Applicant List individually or as one consolidated list of all applicants; as part of the refresh of the Applicant List review in the Hiring Manager Interface. This will also introduce a way to obtain more detailed information on the status of applicant lists and why selections are not made on a Review. | ●○○ | Reviews | TBD | DHS; DOD; DOI; IRS; Treasury
151671 | Purge Staffing Content | Purge staffing content when retention is no longer required by Agency retention policies. | ●○○ | System | TBD | DOD; HHS
226763 | Human Resources Apprentice | Support HR Specialists making minimum qualifications determinations by using artificial intelligence to parse candidate resumes and highlight relevant experience and education. | ●○○ | System | TBD
238250 | Create Purging Process for USA Staffing Records (Phase 1) | Create additional purging and retention fields that will allow users to manage vacancies that will be purged. | ●○○ | System | TBD
261490 | Task Results Field Usability Updates | Improve usability of the Task Results Field to make it clear for customers who do not use TaskUpdate API that they can update this field prior to task completion. | ●○○ | Task | TBD | DHS; VA
276111 | NOR/RSC Codes Video Vignette | Create a video vignette providing an overview of Notice of Results (NOR) message codes and explaining common Record Status Codes (RSC) to applicants so they have a better understanding of both. | ○○○ | Users | 2025-06-20
276088 | Hiring Manager Video Vignette | Add a video vignette that will provide narrated instructions for navigating to a review/assignment and returning the review to HR. | ○○○ | Users | 2025-09-25
263790 | Hiring Manager Video Vignette | Add a video vignette that will provide narrated Hiring Manager guidance to reinforce existing online training and online help content. | ○○○ | Users | 2025-09-30
241764 | AFDW – Rating Combination Reports | Create standard reports using the vacancy and announcement data available from the Applicant Flow Data Warehouse for each rating combination an applicant is to be considered for. | ○○○ | Applicant Flow Data Warehouse | TBD
154230 | Add Nature of Action Codes to Certificates | Add relevant Nature of Action codes to the Certificate audit process. The codes will transfer to the New Hire record upon creation to better inform onboarding specialists of the nature of the processing action. | ○○○ | Certificate | TBD | DOD; DOI; DOL; Treasury; USDA; VA
155497 | Refresh Hiring Manager User Interface: Position Description Reviews | Merge the PD Review capabilities into the new Hiring Manager interface. | ○○○ | Classification | TBD
155431 | Capture Interview Status by List | Allow a Hiring Manager to record and HR to view if a referred Applicant was interviewed on one or more applicant lists on an Applicant List Review. | ○○○ | Hiring Manager | TBD | DHS; DOD; DOL; HHS; IRS; NLRB; Treasury; USAID; USDA
262932 | Remove Candidates from User Boards When They Become Unavailable in Candidate Inventory | Automatically remove candidates from user boards as they become unavailable, so managers do not continue to see applicants they were interested in but can no longer hire. | ○○○ | Hiring Manager | TBD
151674 | Purge New Hire Records | Permanently delete new hire records following the completion of the Onboarding process and in line with eOPF data retention policies. | ○○○ | New Hire | TBD | DOD; HHS
153115 | Improve HM User Notifications | Enable automated system notifications to remind Hiring Managers about coming due or overdue assignments. | ○○○ | Notifications | TBD | DHS; DOD; DOI; DOL; Treasury; USDA; VA
151675 | eVerify Interconnection | Allow HR users to submit a New Hire’s information directly to eVerify without having to log into eVerify (with some exceptions). The interconnection would receive statuses back from eVerify as specific milestones are achieved, automatically closing out system generated tasks as they are completed. | ○○○ | Onboarding | TBD | DHS; DOC, DOD; DOL; HHS; Treasury
151676 | NBIS Interconnection | Allow HR users to submit a New Hire’s information directly to eQIP without having to log into eQIP. The interconnection would receive statuses back from eQIP as specific milestones are achieved, automatically closing out system generated tasks as they are completed. | ○○○ | Onboarding | TBD | DOD; DOI; DOL; HHS; Treasury; VA
245281 | Mass assign/update Process Owner from New Hires Dashboard | Enable users to update the Process Owner for a group of New Hires from the New Hires Dashboard. | ○○○ | Onboarding | TBD
245283 | Reactivate multiple New Hire records from New Hires Dashboard | Enable users to reactivate a group of New Hire records from the New Hires Dashboard. | ○○○ | Onboarding | TBD | USDA
155494 | Refresh Hiring Manager User Interface: Request to Fill Position | Add Request to Fill capabilities into the new Hiring Manager Interface. | ○○○ | Request | TBD
249598 | Change Staffing Approach after Request Is Approved | Allow creation of new vacancies, linking of existing vacancies, or manual creation of new hire records from a Request after its approval, regardless of the initial Request Type selected. The system will assign the appropriate request type based on the outcome of the recruitment. | ○○○ | Request | TBD | DHS; DOD; DOI; DOL; HHS; USDA; VA
252137 | Display "Who to Contact" Information for Requests on the HM Dashboard | Allow Hiring Managers to quickly see on their Dashboard who they can contact when they have questions about a Request. | ○○○ | Request | TBD
155495 | Refresh Hiring Manager User Interface: Panel Reviews | Merge the current Panel Review capabilities into the new Hiring Manager Interface. | ○○○ | Reviews | TBD
155496 | Refresh Hiring Manager User Interface: Announcement Reviews | Merge the current JOA Review capabilities into the new Hiring Manager Interface. Included in this capability refresh will be improvements to the way that statuses are captured and displayed at both the Assignment and Review levels. | ○○○ | Reviews | TBD
151681 | Implement Job Analysis | Utilize existing request, library, task, and review capabilities to manage the job analysis process between the HR Office and Hiring Managers. | ○○○ | Reviews | TBD | DHS; DOI; HHS; VA
185657 | AFD Announcements API Entity | Rewrite & Deploy AFD Announcements API Entity in Azure. | ○○○ | Data API
185658 | AFD Applications API Entity | Rewrite & Deploy AFD Applications API Entity in Azure. | ○○○ | Data API
326014 | AFD Vacancies API Entity | Rewrite & Deploy AFD Vacancies API Entity in Azure. | ○○○ | Data API
100422 | Applicant Flow Data App | Publish a Applicant Flow Data App. | ○○○ | Power BI
146298 | Add Email Address to User Drop-down Lists | Adds a visible and searchable email address to user drop down lists so that users may easily differentiate between staff members with similar or identical names. | ●●● | Request | 2024-10-18 | USDA
261861 | Resolve Accessibility Issues within Hiring Manager Reviews | Address known accessibility issues and improve the ability of all Hiring Manager users to successfully use Hiring Manager Reviews. | ●●● | Hiring Manager | 2024-11-14
249486 | Add saved search capabilities to Advanced Search | Allow Human Resources and Onboarding users to save named sets of filter/search criteria in Advanced Search so they can quickly search vacancies, announcements, position descriptions, and more without having to manually reenter the criteria each time. | ●●● | Search | 2024-11-14
350750 | Link Hiring Manager to new online help pages | Update all Hiring Manager context-sensitive online help references and links to direct users to the new Zendesk help platform, as an initial step in migrating all USA Staffing help content to this improved platform. | ●●● | Hiring Manager | 2025-01-09
245280 | Send Onboarding Notifications to multiple New Hires from Dashboard | Enable users to send Onboarding Notifications to a group of New Hires from the New Hires Dashboard. | ●●● | Onboarding | 2025-01-09 | DHS; DOI; IRS; Treasury
251132 | Change Requester/Hiring Manager on a Request After Approval | Enable HR users to change the assigned Requester throughout the lifecycle of the request and allow customers to keep Requests current as personnel and associated work assignments change during a hiring action. | ●●● | Request | 2025-01-09 | DOI; IRS; NASA; Treasury; VA
224015 | Enable Multiple RPI Vendors in USAS Organizations | Allow for multiple RPI vendors within an Organization to accommodate agencies that use multiple personnel systems. | ●●● | RPI | 2025-01-09 | DHS; DOD; DOI; IC; Treasury; USAID
239847 | Add Benefits Section to Announcement | Adds the Benefits section to the Announcement Text page and Announcement Templates in alignment with USAJOBS. | ●●● | Announcement | 2025-02-06
239383 | Update Filter Layout on Vacancies Dashboard | Enhance user experience and usability by replacing filters on the Vacancy dashboard with newly designed filter side drawer that contains expandable/collapsible sections, and adding new filter options. | ●●● | Dashboard | 2025-02-06 | DOD; DOI; DOJ; USDA; VA
354656 | Create Additional Selection Request - Manual Request Numbers | Grant HR users the ability to manually enter Request Numbers when creating and approving Additional Selection requests in bulk within a Certificate. | ●●● | Request | 2025-02-06 | DOD; DOI; DOL; IRS; NASA; Treasury; USDA
152170 | Add RPI Event History Log | Allow users with specific permissions the ability to see, sort, and resend task and request status events from an RPI Event History Log for all request types. | ●●● | RPI | 2025-02-06 | NASA; VA
138939 | Improve Individual Selection Tracking | Allow Hiring Managers and HR users to more easily indicate an individual/early selection from a Certificate to improve collaboration, tracking, and reporting. | ●●● | Certificate | 2025-03-06 | SSA; VA
101129 | Time to Hire App | Publish a Time to Hire App. | ●●● | Power BI | Q1 FY25
100195 | New Hire App | Publish a New Hire App. | ●●● | Power BI | Q1 FY25
253686 | Certificate App | Publish a Certificate App. | ●●● | Power BI | Q2 FY25
| USA Staffing

## FY24 Features
Key
Complete | ●●●
Number | Name | Description | Phase | Area | Production Delivery Target | Interested Agencies
226800 | Power BI: MVP1 – User License | Publish a User License Power BI app, which will be initially available to customers in Power BI via the Microsoft Authenticator app. | ●●● | Power BI | 2023-08-01
151677 | Create New Hire Activity Summary | Enable automated system notifications to warn New Hire users about coming due or overdue task assignments. | ●●● | New Hire | 2023-10-06 | DHS; DOI; USDA
237742 | HDW – Request Process Owner Reporting | Enable reporting on the Request Process Owner field. | ●●● | Hiring Data Warehouse | 2023-10-11
251681 | HDW - Task Owner Reporting | Enable enhanced reporting on staffing and onboarding task owners | ●●● | Hiring Data Warehouse | 2023-10-25
252931 | HDW - NH Activity Summary Reporting | Enable reporting on the New Hire Activity Summary toggle. | ●●● | Hiring Data Warehouse | 2023-10-25
246102 | HDW - Candidate Inventory Reporting (Phase 1) | Enable reporting on Candidate Inventory and update standard reports. | ●●● | Hiring Data Warehouse | 2023-11-01
228218 | Improve Requests Approval Process | Enhance system handling of the Request approval process to prevent potential data inconsistencies. | ●●● | Request | 2023-11-03
225139 | Increase USA Hire Applicant Status Transparency | Provides HR users greater transparency into applicants' USA Hire status, including score details and indicators for whether or not assessments have been completed. | ●●● | USA Hire | 2023-11-03
249754 | HDW - USA Hire Status Reporting | Enable reporting on USA Hire Status fields. | ●●● | Hiring Data Warehouse | 2023-11-29
155339 | Create Locations Bundle Library | Add a new administrative library for bundling and assigning pre-defined groups of Announcement Locations into an announcement. | ●●● | Administration | 2023-12-01 | DOC; DOD; Peace Corps; Treasury; VA
218328 | Improve Request Process Owner Management | Enable HR users to better organize, track, and distribute requests through additional request fields and improvements to the existing Request Dashboard. | ●●● | Request | 2023-12-01 | HHS; Treasury; USDA; VA
255248 | HDW - USA Hire Reporting Enhancements | Add reporting on additional assessment and USA Hire elements. | ●●● | Hiring Data Warehouse | 2023-12-06
244201 | FootPrints Multi-Factor Authentication (MFA) | Encapsulate FootPrints behind MFA for enhanced security. | ●●● | Authentication | 2023-12-31
256416 | Online Training Multi-Factor Authentication (MFA) | Encapsulate online training platform behind MFA for enhanced security. | ●●● | Authentication | 2023-12-31
154900 | Add Request Event Log to Hiring Manager Dashboard | Provide greater detail about the state of each 'Request to Fill Position' to the new Hiring Manager Dashboard. | ●●● | Hiring Manager | 2024-01-05 | DOD; DOI; HHS; Treasury; VA
151678 | Candidate Inventory (MVP) | Give HR users and Hiring Managers access to a filterable list of applicants that have been previously identified as qualified candidates on a Certificate within that organization. Hiring Managers may search the inventory by Series, Grade, and Location to look for applicants to consider prior to initiating a new announcement. | ●●● | Hiring Manager | 2024-01-05 | DOD; DOE; IC; NASA; OPM; VA
258587 | HDW - Locations Bundle Reporting | Add reporting on locations bundles. | ●●● | Hiring Data Warehouse | 2024-01-31
256089 | Update Vacancies on a Request After Approval | Allow HR users to update the number of vacancies on any request type after approval. | ●●● | Request | 2024-02-02 | IRS; Treasury
258606 | HDW - Request Vacancies Reporting | Make request vacancies and changes reportable. | ●●● | Hiring Data Warehouse | 2024-02-14
266302 | HDW - Narrative Follow-up Reporting | Make narrative follow-up parent items identifiable. | ●●● | Hiring Data Warehouse | 2024-02-28
267026 | HDW - Prior Federal Service Reporting | Make some applicant form responses related to prior federal service reportable. | ●●● | Hiring Data Warehouse | 2024-02-28 | USDA
259325 | Update 2024 State Tax Forms | Make all necessary updates to individual state tax forms to match new state issued versions as they are released at the beginning of the new calendar year. | ●●● | Forms | 2024-03-01 | Multi-Agency
260946 | Add Assessment Numbering in Hiring Manager Reviews | Adds the number associated with each item in the assessment questionnaire so Hiring Managers can easily collaborate with HR as assessments and applications are reviewed. | ●●● | Hiring Manager | 2024-03-01 | IRS; Treasury
261866 | Resolve Accessibility Issues with HR Review Pages | Address known accessibility issues and improve all capabilities for HR Users to successfully use HR Review pages. | ●●● | Reviews | 2024-03-01
244154 | USA Staffing Login Chatbot | Add a USA Staffing login chatbot that users can interact with for guided 24/7 login assistance. | ●●● | Users | 2024-03-01
260990 | New Hire Overview Redesign | Move certain data points from the Overview page to the header to enhance visibility of key information across the New Hire record. | ●●● | New Hire | 2024-03-29
259020 | Tasks Dashboard Pagination | Add pagination to Tasks Dashboard to help users better manage filters and results on this page. | ●●● | Dashboard | 2024-04-26
155340 | Create Hiring Paths Bundle Library | Add a new administrative library for bundling and assigning pre-defined groups of Hiring Paths into an announcement. | ●●● | Administration | 2024-05-31 | DOD
253965 | Implement Saved Searches for Candidate Inventory | Allows a Hiring Manager to save named sets of filter/search criteria, so they can quickly search for candidates using the same criteria in the future without having to manually reenter the criteria each time. | ●●● | Hiring Manager | 2024-05-31 | Multi-Agency; VA
243971 | Create New RPI Objects for Task and Request Status Updates | Expand data elements sent to customers via the Request Processing Interconnection (RPI). A new section, titled RPIUpdates, will be added to the XML for both Request and Task Updates, including new XML objects for Request, Task, New Hire, and Vacancy. These elements will provide information presently served via Data Self Service (DSS) to ease the transition when DSS is decommissioned. | ●●● | RPI | 2024-05-31 | DHS; DOD; NASA; USDA; VA
259009 | Allow Users to Retrigger call to UpdateAPI | Grant users the ability to do a one-time attempt to retrieve a response from a system interconnection when an error was received for the Verify Selective Service System Registration onboarding task. | ●●● | Interconnections | 2024-06-28
261287 | Verification Question Item Validator | Create a new "Verification" validator type for new hire questionnaire item(s) to allow comparison between two fields. | ●●● | New Hire | 2024-06-28 | USDA
245225 | Update Advanced Search | Redevelop Advanced Search to include a new user interface, extensive performance improvements, and the ability for users to modify their results options. | ●●● | Search | 2024-06-28 | HHS
244196 | USA Staffing Login Video Vignette | Add a video vignette that will provide narrated login guidance to reinforce existing online training and online help content. | ●●● | Users | 2024-06-28
155257 | Structured Resume Review Refinements | Adjust Structured Resume Review logic to better communicate applicant status and account for HR adjudications on screen-outs related to eligibility and conditions of employment. | ●●● | Reviews | 2024-08-23 | DOE; HHS; Treasury
259563 | Add Multi-Select Filtering Options to Tasks and New Hires Dashboard | Allow users to select multiple options on certain fields when filtering on the Tasks and New Hires dashboards to improve usability around managing new hires. | ●●● | Dashboard | 2024-09-20 | DOD; VA
146068 | Expand Additional Selection Request Creation from Certificate | Grant HR users the ability to create and approve requests in bulk within a certificate (increasing from 10 to 100) and improve performance. | ●●● | Request | 2024-09-20 | DOD; IRS; NASA; Treasury
138937 | Separate Create and Edit Request Permission | Separate the ability to create a request and edit a request so that customers may require the use of RPI or limit who may create a request. | ●●● | Request | 2024-09-20 | USDA; VA
138941 | Accept linked Vacancies for Requests created via RPI | Allow agencies to send Vacancy and Workflow information associated with an Additional Selection Request over the Request Processing Interconnection to expedite request approval. | ●●● | RPI | 2024-09-20 | NASA; Treasury; VA
263870 | HDW - Rating Combinations Reporting Updates | Facilitate rating combination reporting for vacancies where assessment rating combinations differ from the linked position description's combinations. | ●●● | Hiring Data Warehouse | 2024-09-25 | VA
263884 | HDW - Application Marked as Reviewed Reporting | Make information related to an application being 'marked as reviewed' reportable. | ●●● | Hiring Data Warehouse | 2024-09-25
| USA Staffing

## FY23 Features
Key
Complete | ●●●
Number | Name | Description | Phase | Area | Production Delivery Target | Interested Agencies
155519 | Enable Verify New Hire Task Status Reset | Allow Office Administrators the ability to reset an erroneously completed 'Verify the New Hire Arrived for Their First Day of Duty' task status. | ●●● | Onboarding | 2022-10-21 | DOD
6235/6238 | HDW – Remote Job | Enable reporting on remote job settings in the request, vacancy, and announcement areas. Additional characteristics of vacancies and vacancy settings, such as occupational specialty codes, vacancy hyperlinks, and concatenated position description titles, will also be made reportable. | ●●● | Hiring Data Warehouse | 2022-11-09
221238 | Create Selections Page for Vacancies | Allow HR users to have one central page where they can easily see all selections made from certificates issued for a Vacancy, the status of each selection, and key details about the new hire records if any have been created. | ●●● | Certificates | 2022-11-18
218314 | HDW – Application Notification Metrics | Develop pre-built metrics related to application notifications, including the identification of which and how many applications should receive each notification type and how many have been sent. | ●●● | Hiring Data Warehouse | 2022-12-07
152819 | New Hire Interconnection Status Receipt (i.e., Task Update API) | Enable USA Staffing to collect and process incoming task status and task results updates from the interconnected HRIT systems so that corresponding changes to USA Staffing tasks may be made automatically. | ●●● | Onboarding | 2022-12-21 | NASA
6235 | HDW - Request Schedules and Workflows | Enable reporting on request work schedules and workflows in the Hiring Data Warehouse. | ●●● | Hiring Data Warehouse | 2023-02-01
213061 | HDW – New Hire Contacts | Enable reporting on all new hire contact types in the Hiring Data Warehouse. | ●●● | Hiring Data Warehouse | 2023-02-01
214216 | HDW – Location Labels | Enable reporting on location label information throughout all areas of the hiring data warehouse, including application locations, request locations, and applicant list/certificate filters. | ●●● | Hiring Data Warehouse | 2023-02-15
151673 | Include New Hire Details in Core Activity Summary | Add content to the Activity Summary emails sent to HR and Onboarding Only users to provide updates on New Hire records for which they are the Process Owner. | ●●● | Activity Summary | 2023-02-17 | DHS; HHS; VA
229806 | Update 2023 State Tax Forms | Make all necessary updates to individual state tax forms to match new state issued versions as they are released at the beginning of the new calendar year. | ●●● | Forms | 2023-02-17
11743 | AFDW – Rating Combos | Enable the same vacancy and announcement data available from the AFD Vacancy feature for each rating combination an applicant is to be considered for. | ●●● | Applicant Flow Data Warehouse | 2023-03-01
6568 | HDW - Notes and Documents | Enable reporting on new Notes and Documents data beyond current Staffing Reports fields in the HDW. | ●●● | Hiring Data Warehouse | 2023-03-15
154614 | Include CHCO Survey in Certificate Reviews | Embed the new and improved CHCO survey into the Hiring Manager’s user flow when returning Certificate Reviews. The new survey will replace the currently published link that takes you to the legacy CHCO survey. | ●●● | Hiring Manager | 2023-04-14 | DHS; DOD
154504 | Integrate Structured Resume Review (i.e., Subject Matter Expert Evaluation) into USA Staffing | Enable agency subject matter experts (SMEs), using USA Staffing’s Hiring Manager interface, to evaluate applicant resumes and qualify applicants for consideration under a new 'SME Evaluation' Assessment Type. | ●●● | Reviews | 2023-04-14 | Multi-Agency
214242 | HDW – Hurdles | Enable reporting on the use of hurdled assessment processes in the hiring data warehouse. | ●●● | Hiring Data Warehouse | 2023-05-10
235019 | Data APIs - Filter by DW Last Modified Date | Implement new filters using the start and end date range of the Data Warehouse Last Modified Date for each record. | ●●● | Data APIs | 2023-06-21
238278 | Copy Assessment Packages From Previous Vacancy | Allow HR users with the appropriate permission to copy an Assessment Package from one Vacancy to another. This feature excludes USA Hire assessments. | ●●● | Assessment Package | 2023-07-07 | DOD; HHS
246102 | HDW – Candidate Inventory Reporting Phase 1 | Enable reporting on Candidate Inventory at the vacancy, application, and certificate levels. | ●●● | Hiring Data Warehouse | 2023-08-02
238567 | APIs – Update Snapshot Value Functionality | Create a rotating snapshot value that can be queried. | ●●● | Data APIs | 2023-08-16
6237 | HDW – Reviews | Add Review Followers and Reviewer Assignments into the hiring data warehouse. | ●●● | Hiring Data Warehouse | 2023-08-16
247730 | HDW - USA Hire Attributes Reporting | Enable reporting on USA Hire Attributes field at the Vacancy level. | ●●● | Hiring Data Warehouse | 2023-08-30
247730 | HDW - USA Hire Attributes | Enable reporting on USA Hire Attributes fields. | ●●● | Hiring Data Warehouse | 2023-08-30
246580 | HDW - Assessment Questionnaire New Reporting | Enable reporting on AQ Assessment Methods, Assessment Flags, and other new fields. | ●●● | Hiring Data Warehouse | 2023-09-13
| USA Staffing

## FY22 Features
Key
Complete | ●●●
Number | Name | Description | Phase | Area | Production Delivery Target | Interested Agencies
6765 | HDW - Workload Assignments | Enable reporting on workload assignments in the Hiring Data Warehouse. | ●●● | Hiring Data Warehouse | 2022-04-07
120940 | Update 2022 State Tax Forms | Make all necessary updates to individual state tax forms to match new state issued versions as they are released at the beginning of the new calendar year. | ●●● | Forms | 2022-04-08
154176 | Add Onboard New Hire Request Type & Fields to RPI | Allow agencies to submit 'Onboard New Hire' and 'Additional Selection' Requests via RPI, including New Hire data required to approve the request. | ●●● | RPI | 2022-04-08 | NASA
154410 | Update Documents in New Hire Area | Allow HR and Onboarding users to leverage Applicant document management tools like drag and drop and pulling in files from other locations in USA Staffing from a New Hire record. | ●●● | Onboarding | 2022-05-06
155022 | Add Remote Work Option to Announcement | Allow announcements to be posted to USAJOBS advertising the position as 'Remote' in line with the recently updated OPM guidance for telework and remote work. | ●●● | Announcement | 2022-06-03 | VA
152160 | Selective Service Interconnection | Allow HR Users to submit a New Hire’s information directly to the Selective Service to verify registration requirements. The interconnection would receive statuses back from Selective Service, automatically closing out system generated tasks as they are completed. | ●●● | Onboarding | 2022-06-03
154569 | Add Custom Onboarding Contacts | Enable agencies to create additional custom onboarding contacts beyond the HR, Payroll, and Benefit Contacts already available in the New Hire record. | ●●● | Onboarding | 2022-06-30 | DHS; HHS; USDA; VA
154990 | Enable Edit of Individual Competencies in Network Library | Allow administrators to view and edit individual competencies within the Manage Competency Network section in Admin. | ●●● | Competency/Item Library | 2022-07-29 | NASA
| API – Applicant Flow Data | Enable interconnected systems to pull Applicant Flow Data from the Metrics Data Warehouse. | ●●● | Data APIs | 2022-08-03
6234 | HDW – Assessment | Enable reporting on external job analysis outputs and sources, and details about assessments in a vacancy including the assessment plan, scoring protocol, screen-out items, and categories. | ●●● | Hiring Data Warehouse | 2022-08-03
154484 | Replace Password Login with Login.gov | Change the alternate authentication mechanism into USA Staffing from username and password to Login.gov. PIV/ CAC will remain the standard authentication mechanism for USA Staffing users logging into their accounts. | ●●● | Users | 2022-08-03
10115 | AFDW – Vacancy | Move existing Applicant Flow Data reporting to the Applicant Flow Data Warehouse and add additional announcements, certificate level data, and a unique applicant identifier. | ●●● | Applicant Flow Data Warehouse | 2022-08-31
151672 | Automate Hurdle Criteria | Create the ability to structure an Assessment Package where an HR user can define a process for how an applicant can automatically continue through a multi-step hiring process based on the applicant’s Assessment results. | ●●● | Assessment Package | 2022-09-23 | DHS; DOI; HHS; NASA; Treasury; VA
154317 | Redesign the Hiring Manager Dashboard | Update the Hiring Manager’s interface to make it easier for HM users to identify items requiring attention and allow for more robust tracking of Hiring Actions and New Hires. | ●●● | Hiring Manager | 2022-09-23 | DOD
215140 | Automate USA Hire Reminder Notifications | Create the ability to automatically send a reminder notification to any remaining PA applicants once the Announcement has closed to encourage them to complete the USA Hire Assessments. | ●●● | USA Hire | 2022-09-23 | DHS
| USA Staffing

## Epics (hidden)
Key
Started | ●○○
In Progress | ●●○
Complete | ●●●
New Feature
Item # | Item Name | Item Description | Interested Agencies | State | Module | Target Date to Prod
2 | Structuerd Resume Review | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOI | ○○○ |  | TBD
6 | Feature #6 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DHS | ●○○ |  | TBD
9 | Feature #9 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOI, DOD, TREASURY | ●●○ |  | TBD
#154900 | Request Event Log to HM Dashboard | This feature iterates on the Hiring Manager Dashboard and adds new activity/event logging for each Hiring Action the manager has access to. | DOD, DOI, HHS, VA | ●○○ |  | TBD
8 | Feature #8 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOE, VA | ●●○ |  | 2024-08-03
7 | Feature #7 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | VA | ●○○ |  | 2024-07-03
5 | Feature #5 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | TREASURY, VA | ●●○ |  | 2024-05-03
4 | Feature #4 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOE, DOI, DHS, VA, | ●○○ |  | 2024-04-03
3 | Feature #3 | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOE, DOI | ●●○ |  | 2024-03-03
1 | Candidate Inventory | Lorem ipsum dolor sit amet, consectetur adipiscing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Aliquam faucibus purus in massa tempor nec feugiat nisl. Tellus orci ac auctor augue mauris. Volutpat commodo sed egestas egestas fringilla phasellus faucibus. | DOE | ●○○ |  | 2024-01-03